## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Progress
Office Setup & Renovation | 2024-06-01 | 2024-06-15 | 15 | In Progress
IT Infrastructure Installation | 2024-06-10 | 2024-06-25 | 16 | In Progress
Employee Onboarding | 2024-06-18 | 2024-06-30 | 13 | In Progress
Office Equipment Procurement | 2024-06-01 | 2024-06-17 | 17 | Completed
Security System Installation | 2024-06-14 | 2024-06-28 | 15 | Delayed
Marketing Launch Campaign | 2024-07-01 | 2024-07-15 | 15 | In Progress
Total Tasks: |  |  | 71 | 4/6 Active