## Worksheet
Office Management - Gantt Chart Summary View
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
01.01 | Office Space Preparation | Facilities Team | 2023-10-05 | 2023-10-15 | In Progress | 65%
01.02 | Purchase Office Equipment | Procurement Team | 2023-10-10 | 2023-10-25 | In Progress | 45%
01.03 | Network & System Setup | IT Department | 2023-10-12 | 2023-10-30 | In Progress | 75%
01.04 | Hire & Train Staff | HR Department | 2023-10-15 | 2023-11-30 | Pending | 5%
01.05 | Acquire & Deploy Licenses | IT Department | 2023-10-18 | 2023-11-5 | In Progress | 90%
Overall Project Summary (Phase 1: Office Setup) | [5 empty] | 62%
Gantt Chart Timeline (Summary View)
Timeline Overview |  | [===¦==¦====¦=========¦======================] 10/5 10/10 10/15 10/25 Nov