## Worksheet
Office Management Monthly Planner - Analysis View
Task / Project | Department | Key Dates |  |  |  | Responsible Team | Status
|  | Start Date | Target Completion | Actual Completion | Duration (Days)
Q3 Strategic Planning | Executive Office | 2024-09-01 | 2024-10-15 | 2024-10-13 | 43 | Exec Team + HR | Completed
Annual Office Audit | Finance & Admin | 2024-09-10 | 2024-10-31 | 2024-10-31 | 52 | F&A Team | Completed
IT Infrastructure Upgrade | IT Department | 2024-09-15 | 2024-11-30 | - | - | IT Team Lead | In Progress
Employee Performance Reviews | HR Department | 2024-09-05 | 2024-11-30 | - | - | HR Managers | In Progress
Office Space Redesign (Phase 1) | Facilities Management | 2024-09-20 | 2024-10-31 | - | - | F&M Team + Designers | In Progress
Vendor Contract Renewals | Procurement | 2024-10-01 | 2024-11-30 | - | - | Purchasing Team | In Progress
Annual Training Program Launch | Learning & Development | 2024-09-15 | 2024-11-30 | - | - | L&D Team + Dept. Heads | In Progress
Security System Enhancement | Safety & Security | 2024-09-10 | 2024-11-30 | - | - | Security Unit + IT | Delayed (Pending Approval)
Total Tasks: |  | 8 | 6 | 5 | Total Duration (Avg): 41.9 days | Summary Status: 62.5% Complete, 1 Delayed Task