## Worksheet
Advanced Project Plan
Office Management ¦ Q3 2024 Implementation
Task ID | Task Description | Owner | Start Date | End Date | Status | % Complete | Budget (USD)
OP-001 | Office Space Assessment & Planning | Alice Johnson | 2024-07-01 | 2024-07-15 | In Progress | 65% | $8,500
OP-002 | IT Infrastructure Upgrade | Robert Chen | 2024-07-10 | 2024-08-31 | In Progress | 45% | $35,750
OP-003 | Furniture Procurement & Delivery | Sarah Kim | 2024-08-15 | 2024-09-15 | Pending | 0% | $18,900
OP-004 | Employee Onboarding Process Design | Daniel Rodriguez | 2024-07-18 | 2024-08-15 | Completed | 100% | $5,600
OP-005 | Security System Installation | Linda Thompson | 2024-08-31 | 2024-10-15 | Pending | 0% | $16,850
OP-006 | Facility Maintenance & Cleaning Schedule | Maria Garcia | 2024-09-15 | 2024-11-30 | Pending | 0% | $7,350
OP-007 | Energy Efficiency Audit & Optimization | Tom Wilson | 2024-10-01 | 2024-11-30 | Pending | 0% | $9,855
OP-008 | Office Culture & Wellness Initiative Launch | Jennifer Lee | 2024-11-01 | 2024-12-31 | Pending | 0% | $6,550
Total Project Budget: | [6 empty] | $109,355