## Worksheet
Office Management - Project Plan (Analysis View)
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
P001 | Project Initiation & Planning | John Smith | 2024-05-01 | 2024-05-15 | On Track | 95%
P002 | Resource Allocation Review | Sarah Johnson | 2024-05-16 | 2024-05-31 | On Track | 80%
P003 | Office Space Optimization Analysis | Mike Davis | 2024-06-01 | 2024-06-15 | On Track | 35%
P004 | Equipment Inventory Audit | Lisa Wong | 2024-06-16 | 2024-07-15 | On Track | 15%
P005 | Workflow Process Mapping | David Lee | 2024-07-16 | 2024-08-31 | Delayed | 5%
P006 | Implementation Strategy Finalization | Emma Clark | 2024-09-01 | 2024-11-30 | Completed | 100%
P007 | Staff Training Program Development | Tom Harris | 2024-12-01 | 2025-01-31 | Delayed | 0%
Analysis View - Project Plan (Office Management)
Last Updated: May 5, 2024 ¦ Generated from Office Management System