## Worksheet
Office Management - Project Plan
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | % Complete
TASK001 | Office Space Setup and Layout Design | Jane Smith | 2023-10-01 | 2023-10-15 | In Progress | 65%
TASK002 | Furniture Procurement and Delivery | Mike Johnson | 2023-10-10 | 2023-11-05 | In Progress | 45%
TASK003 | IT Infrastructure Installation | Lisa Brown | 2023-10-15 | 2023-11-10 | To Do | 0%
TASK004 | Network and Security Configuration | David Lee | 2023-11-05 | 2023-11-20 | To Do | 0%
TASK005 | Employee Onboarding and Training | Sarah Wilson | 2023-11-15 | 2023-11-30 | To Do | 0%
TASK006 | Final Inspection and Handover | James Carter | 2023-11-25 | 2023-11-30 | To Do | 0%
Total Tasks: | [5 empty] | 6
Legend:Status options include 'To Do', 'In Progress', and 'Completed'. Use % Complete to track progress.