## Worksheet
Office Management - Project Plan (Client View)
Project: Office Renovation & Relocation
Client: Global Solutions Inc.
Phase | Task | Start Date | End Date | Assigned To | Status | Budget (USD)
Phase 1: Planning & Approval | Define renovation scope and requirements | Apr 05, 2025 | Apr 12, 2025 | Jane Smith (Project Manager) | In Progress | $15,000
| Prepare design proposals and mockups | Apr 13, 2025 | Apr 19, 2025 | Mike Johnson (Lead Designer) | In Progress | $8,000
| Client review and approval of design concepts | Apr 20, 2025 | Apr 26, 2025 | Jane Smith (Project Manager) | In Progress | $3,000
| Finalize project budget and timeline approval | Apr 27, 2025 | May 03, 2025 | Jane Smith (Project Manager) | In Progress | $4,000
Phase 2: Procurement & Logistics | Source and order office furniture and fixtures | May 04, 2025 | May 18, 2025 | Sarah Lee (Procurement Specialist) | Delayed | $60,000
| Arrange equipment installation schedule and contractors | May 19, 2025 | May 25, 2025 | Derek Brown (Logistics Coordinator) | In Progress | $18,000
| Confirm delivery dates and storage for interim relocation | May 26, 2025 | Jun 01, 2025 | Sarah Lee (Procurement Specialist) | Delayed | $6,500
Phase 3: Construction & Setup | Demolition of old office space | Jun 02, 2025 | Jun 06, 2025 | TechBuild Inc. (Contractor) | Completed | $14,000
| Electrical and network infrastructure installation | Jun 07, 2025 | Jun 14, 2025 | TechBuild Inc. (Contractor) | In Progress | $38,000
| Installation of new office furniture and fixtures | Jun 15, 2025 | Jun 21, 2025 | TechBuild Inc. (Contractor) | Delayed | $47,000
| Final inspection and client sign-off | Jun 22, 2025 | Jun 30, 2025 | Jane Smith (Project Manager) | In Progress | $7,500
Phase 4: Relocation & Handover | Move equipment and data to new office | Jul 01, 2025 | Jul 05, 2025 | TechBuild Inc. (Contractor) | Delayed | $19,500
| Final handover and training session for staff | Jul 06, 2025 | Jul 12, 2025 | Jane Smith (Project Manager) | In Progress | $9,000
Total Project Budget: | [5 empty] | $317,500
Note:This is a client-facing project plan. All timelines and statuses are subject to change based on external factors.