## Project Plan - Compact Template
Project Plan - Compact Template
Task ID | Task Name | Assigned To | Start Date | End Date | Status | % Complete
P1001 | Project Initiation | Jane Doe | 2023-10-01 | 2023-10-05 | In Progress | 75%
P1002 | Requirement Gathering | John Smith | 2023-10-06 | 2023-10-15 | Not Started | 0%
P1003 | Design Phase | Alice Brown | 2023-10-16 | 2023-10-25 | In Progress | 45%
P1004 | Development | Mike Johnson | 2023-10-26 | 2023-11-30 | Not Started | 0%
P1005 | Testing & QA | Sarah Wilson | 2023-12-01 | 2023-12-15 | Not Started | 0%
P1006 | Deployment | Dave Lee | 2023-12-16 | 2023-12-20 | Not Started | 0%
Overall Progress: | [5 empty] | 34%