## Worksheet
Office Management - Detailed Project Plan
Task ID | Task Description | Owner | Start Date | End Date | Status | % Complete | Budget (USD)
PH1-001 | Project Initiation & Approval | Project Manager | 2023-11-05 | 2023-11-15 | Completed | 100% | $5,000
PH2-101 | Define Project Scope & Objectives | Project Manager | 2023-11-16 | 2023-11-30 | In Progress | 75% | $8,000
PH2-102 | Develop Detailed Work Breakdown Structure (WBS) | Project Manager & Team Leads | 2023-11-30 | 2023-12-15 | In Progress | 65% | $7,500
PH2-103 | Create Project Schedule & Timeline (Gantt Chart) | 2023-12-16 | 2024-01-15 | In Progress | 50% | $9,500
PH2-104 | Resource Allocation & Assignment | 2023-12-16 | 2024-01-31 | In Progress | 45% | $6,800
PH2-105 | Project Plan Finalization & Stakeholder Sign-off | 2024-01-31 | 2024-02-15 | Delayed | 35% | $8,750
PH3-201 | Project Kick-off Meeting | 2024-02-16 | 2024-03-31 | In Progress | 95% | $7,500
PH3-202 | Office Space Setup & Infrastructure Deployment | 2024-03-15 | 2024-05-15 | In Progress | 68% | $89,700
PH3-203 | Hiring & Onboarding New Team Members | 2024-04-15 | 2024-06-30 | In Progress | 87% | $65,300
PH3-204 | IT System Installation & Configuration | 2024-05-15 | 2024-07-15 | In Progress | 63% | $78,900
PH4-301 | Daily Task Tracking & Progress Reports | 2024-03-16 | 2025-07-31 | In Progress | 98% | $36,500
PH4-302 | Budget vs. Actual Cost Analysis | 2024-04-16 | 2025-07-31 | In Progress | 96% | $31,800
PH5-401 | Final Deliverables Submission & Client Acceptance | 2025-06-30 | 2025-07-31 | Delayed | 18% | $49,200
PH5-402 | Project Post-Mortem Review & Lessons Learned | 2025-08-15 | 2025-08-31 | Not Started | 3% | $7,600
PH5-403 | Project Final Report & Documentation Archive | 2025-09-15 | 2025-10-31 | Not Started | 1% | $6,400
Total Project Budget: | [6 empty] | $512,800
Notes:
All dates are in YYYY-MM-DD format.
Status values: "Completed", "In Progress", "Delayed", "Not Started".
Budgets are in USD and include labor, equipment, and overhead costs.
Project end date: 2025-10-31.