## Worksheet
Office Management - Project Plan (Extended)
Task ID | Task Name | Description | Assigned To | Status | Start Date | End Date | Budget (USD)
Project: Office Management Optimization & Infrastructure Upgrade
PM-01 | Needs Assessment & Planning | Conduct office space and workflow analysis to define requirements. | Jane Cooper | Pending | 2024-04-05 | 2024-04-15 | $1,500.00
PM-02 | Workspace Redesign & Layout Planning | Create new office floor plans with ergonomic and collaborative zones. | Luis Mendoza | In Progress | 2024-04-16 | 2024-05-10 | $8,750.00
PM-03 | Furniture Procurement & Delivery | Order and receive new desks, chairs, meeting room furniture. | Sarah Johnson | In Progress | 2024-05-11 | 2024-06-15 | $35,600.00
PM-04 | IT Infrastructure Upgrade | Install new network cabling, Wi-Fi access points, and AV systems. | Marcus Reed | In Progress | 2024-05-15 | 2024-06-30 | $18,950.00
PM-05 | Employee Relocation & Training | Move teams to new space and conduct onboarding sessions. | Jane Cooper | Pending | 2024-07-01 | 2024-07-15 | $3,800.00
PM-06 | Post-Move Evaluation & Feedback Collection | Gather feedback from staff and adjust as needed. | Sarah Johnson | Pending | 2024-07-16 | 2024-07-31 | $1,500.00
Total Project Budget: | [6 empty] | $76,100.00