## Worksheet
Large Business Project Plan
Office Management ¦ Q3 2024
Project Name:Office Modernization & Workflow Optimization
Project Manager:Sarah Thompson
Status:On Track
Budget Allocated:$425,000.00
Start Date:July 1, 2024
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
P-001 | Conduct office space audit and needs assessment | James Reed (Facilities) | 2024-07-01 | 2024-07-15 | In Progress | 85%
P-002 | Design new office layout & workflow zones | Lisa Chen (Design Team) | 2024-07-16 | 2024-07-31 | In Progress | 65%
P-003 | Procure new furniture & equipment | Mark Wilson (Procurement) | 2024-07-18 | 2024-08-15 | Open | 15%
P-004 | Install new IT infrastructure & network upgrades | Alex Morgan (IT Department) | 2024-08-16 | 2024-08-31 | Open | 5%
P-005 | Move employees to new office layout (phased) | Sarah Thompson (Project Lead) | 2024-09-01 | 2024-09-15 | Open | 0%
P-006 | Final inspection & handover to management team | Diana Liu (Quality Assurance) | 2024-09-16 | 2024-09-30 | Open | 0%