## Worksheet
Office Management - Project Plan
Multi-Page Template ¦ Version 1.0 ¦ Prepared for Office Administration
Project Overview
Project Name: | Office Relocation & Infrastructure Upgrade
Project Manager: | Jane Smith
Start Date: | January 10, 2024 |  | End Date: | March 31, 2024
Status: | In Progress (Phase 1)
Priority: | High
Task ID | Task Description | Assigned To | Start Date | End Date | Status
TASK-001 | Conduct site assessment at new office location | Robert Lee, Facilities Team | Jan 10, 2024 | Jan 15, 2024 | In Progress
TASK-002 | Design office layout and workstation placement | Sarah Johnson, Design Team | Jan 16, 2024 | Jan 25, 2024 | To Do
TASK-003 | Procure office furniture and equipment | Mark Williams, Procurement Dept. | Jan 20, 2024 | Feb 5, 2024 | To Do
TASK-004 | Install IT infrastructure (network, cabling, servers) | Lisa Chen, IT Department | Jan 28, 2024 | Feb 15, 2024 | To Do
TASK-005 | Coordinate with vendors for furniture delivery & setup | David Kim, Logistics Team | Feb 10, 2024 | Feb 25, 2024 | To Do
TASK-006 | Finalize move plan and team training sessions | Jane Smith, Project Manager | Feb 20, 2024 | Feb 28, 2024 | To Do
TASK-007 | Execute office relocation (move day) | All Departments | Mar 15, 2024 | Mar 15, 2024 | To Do
TASK-008 | Post-move evaluation and feedback collection | Jane Smith & HR Team | Mar 25, 2024 | Mar 31, 2024 | To Do
Budget Summary (USD)
Category | Planned Budget | Actual Spend | Status
Furniture & Office Equipment | $45,000.00 | $38,250.75 | Under Budget
IT Systems & Cabling | $32,500.00 | $31,890.50 | Under Budget
Professional Moving Services | $28,750.00 | $26,431.25 | Under Budget
Office Layout & Interior Design | $15,000.00 | $14,789.50 | Under Budget
Contingency & Miscellaneous | $12,000.00 | $8,956.30 | Under Budget
Total Project Cost | $133,250.00 | $120,318.30 | Under Budget by $12,931.70
Risk Assessment & Mitigation Plan
Risk ID:RSK-001 | Delays in delivery of office furniture
Description: | Supplier may delay shipment due to shipping issues or manufacturing backlog.
Impact: | High |  | Probability: | Medium
Risk ID:RSK-002 | IT system downtime during move
Description: | Critical servers and network systems may be offline during relocation.
Risk ID:RSK-003 | Staff resistance to new office layout
Description: | Employees may find the new setup less comfortable or productive.
Mitigation & Action Plan
RSK-001: | Negotiate earlier delivery dates, use multiple suppliers for critical items, track shipments weekly.
RSK-002: | Schedule IT migration during weekend; maintain backup systems; test before move day.
RSK-003: | Conduct pre-move surveys, involve team leads in design process, offer workstation adjustment period.