## Worksheet
OFFICE MANAGEMENT PROJECT PLAN
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | % Complete
PM-001 | Project Initiation & Planning | Jane Smith | 2024-01-15 | 2024-01-31 | In Progress | 65%
PM-002 | Resource Allocation & Team Setup | Robert Lee | 2024-01-18 | 2024-02-15 | In Progress | 75%
PM-003 | Office Space Configuration | Lisa Wong | 2024-02-16 | 2024-03-15 | Not Started | 0%
PM-004 | Furniture & Equipment Procurement | David Kim | 2024-02-18 | 2024-03-31 | In Progress | 50%
PM-005 | Cable & Network Installation | Maria Garcia | 2024-03-16 | 2024-04-15 | Not Started | 0%
PM-006 | Software & System Setup | Alex Turner | 2024-03-25 | 2024-05-15 | Not Started | 0%
PM-007 | User Training & Onboarding | Sarah Johnson | 2024-05-16 | 2024-05-31 | Not Started | 0%
PM-008 | Final Inspection & Handover | Jane Smith | 2024-06-01 | 2024-06-15 | Not Started | 0%
Total Tasks | [5 empty] | 8
Average Progress | [5 empty] | 24%