## Worksheet
Office Management - Project Plan (One Page)
Task ID | Task Name | Description | Assigned To | Start Date | End Date | Status
P001 | Office Space Setup | Configure workstations, desks, chairs and IT infrastructure. | Alice Johnson | 2024-10-05 | 2024-10-15 | In Progress
P002 | IT Equipment Procurement | Order laptops, monitors, printers, and networking devices. | Mike Chen | 2024-10-06 | 2024-10-18 | In Progress
P003 | Clean & Sanitize Office Area | Professional cleaning and disinfection of all workspaces. | Sarah Williams | 2024-10-12 | 2024-10-14 | Completed
P004 | Network Configuration | Set up Wi-Fi, security protocols, and access controls. | James Rodriguez | 2024-10-16 | 2024-10-20 | In Progress
P005 | Employee Onboarding Process Design | Create onboarding checklist and training materials. | Lisa Park | 2024-10-17 | 2024-10-25 | In Progress
P006 | Furniture Delivery & Assembly | Deliver and assemble all office furniture as per layout plan. | Tom Bennett | 2024-10-19 | 2024-10-23 | In Progress
P007 | Safety & Compliance Audit | Conduct safety inspections and ensure regulatory compliance. | Elena Foster | 2024-10-24 | 2024-10-30 | Delayed
Project Duration:October 5, 2024 – October 31, 2024
Total Tasks:7 ¦Completed:1 ¦In Progress:5 ¦Delayed:1