## Worksheet
Office Management - Project Plan (Planning View)
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Budget (USD) | Progress (%)
#P001 | Define Project Scope and Objectives | John Smith | 2024-04-01 | 2024-04-05 | In Progress | $1,500.00 | 65%
#P002 | Develop Office Layout Plan | Sarah Johnson | 2024-04-06 | 2024-04-15 | Pending | $3,200.00 | 15%
#P003 | Procure Office Furniture and Equipment | Mike Rodriguez | 2024-04-16 | 2024-05-15 | Pending | $18,500.00 | 3%
#P004 | Install Network and IT Infrastructure | Aisha Patel | 2024-05-16 | 2024-06-30 | Pending | $8,750.00 | 1%
#P005 | Conduct Team Training and Onboarding | Lisa Chen | 2024-07-01 | 2024-07-15 | Pending | $3,800.00 | 5%
#P006 | Final Inspection and Handover to Management | Robert Kim | 2024-07-16 | 2024-07-31 | Pending | $1,950.00 | 8%
Total Budget: | [5 empty] | $37,700.00 | 15% Average Progress