## Worksheet
Project Plan - Office Management
Task ID | Task Name | Description | Assigned To | Status | Start Date | End Date
T001 | Office Space Assessment | Conduct a comprehensive review of current office layout and space utilization. | Alice Johnson | In Progress | 2023-10-01 | 2023-10-15
T002 | IT Infrastructure Upgrade | Upgrade network systems, install new servers, and ensure cybersecurity protocols. | Robert Chen | To Do | 2023-10-16 | 2023-11-30
T003 | Furniture Procurement | Select and order ergonomic office furniture for new workstations. | Emily Rodriguez | Completed | 2023-11-01 | 2023-11-08
T004 | Employee Onboarding Program Revamp | Develop updated onboarding materials and training modules. | Marcus Lee | In Progress | 2023-10-20 | 2023-12-15
T005 | Green Office Initiative Launch | Implement recycling, energy-saving measures, and sustainable office practices. | Sarah Thompson | To Do | 2023-11-10 | 2024-01-31
Total Tasks: |  |  |  |  | 5