## Worksheet
Project Task | Responsible Person | Start Date | End Date | Status | Progress (%)
Project Initiation | John Smith | 2024-01-05 | 2024-01-10 | Completed | 100%
Requirements Gathering | Jane Doe | 2024-01-11 | 2024-01-20 | In Progress | 65%
Design Phase | Mike Brown | 2024-01-21 | 2024-02-05 | Not Started | 0%
Development Phase | Sarah Wilson | 2024-02-06 | 2024-03-15 | Not Started | 0%
Testing & QA | David Lee | 2024-03-16 | 2024-03-31 | Not Started | 0%
Deployment | Laura Garcia | 2024-04-01 | 2024-04-15 | Not Started | 0%
Project Review & Closure | John Smith | 2024-04-16 | 2024-04-30 | Not Started | 0%