## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Progress (%)
T001 | Project Initiation | Jane Smith | 2024-04-01 | 2024-04-05 | In Progress | 75
T002 | Requirement Gathering | Mike Johnson | 2024-04-06 | 2024-04-15 | To Do | 0
T003 | Design Phase | Sarah Lee | 2024-04-16 | 2024-04-30 | To Do | 0
T004 | Development Sprint 1 | David Brown | 2024-05-01 | 2024-05-15 | To Do | 0
T005 | Testing Phase | Alice White | 2024-05-16 | 2024-06-15 | To Do | 0
T006 | User Training & Documentation | Linda Garcia | 2024-06-16 | 2024-06-30 | To Do | 0
T007 | Project Closure & Review | Jane Smith | 2024-07-01 | 2024-07-15 | To Do | 0