## Worksheet
Weekly Project Plan - Office Management
Week Ending | Project Phase | Task Description | Owner | Status | Start Date | End Date | Budget (USD)
2024-04-05 | Planning | Define project scope and objectives | Jane Smith | Completed | 2024-03-15 | 2024-03-18 | $500.00
2024-04-12 | Planning | Identify key stakeholders | Mike Johnson | In Progress | 2024-03-19 | 2024-03-25 | $350.00
2024-04-19 | Execution | Develop office workflow documentation | Sarah Lee | Pending | 2024-03-26 | 2024-04-15 | $800.00
2024-04-26 | Execution | Implement new office software system | Tom Brown | Pending | 2024-03-31 | 2024-05-10 | $3,500.00
2024-05-17 | Monitoring & Evaluation | Conduct team feedback session | Jane Smith | Pending | 2024-04-16 | 2024-05-17 | $600.00
2024-05-31 | Closure | Finalize project report and handover | Mike Johnson | Pending | 2024-05-18 | 2024-05-31 | $750.00
Total Estimated Budget: | [6 empty] | $6,500.00