## Worksheet
Office Management - Project Template (Manager View)
Project ID | Project Name | Department | Start Date | End Date | Status | Budget (USD)(Allocated) | Budget Used (USD)(Actual) | Progress (%)(Overall) | Manager
PJ001 | Office Renovation 2024 | Facilities | Jan 15, 2024 | Apr 30, 2024 | In Progress | $150,000 | $78,500 | 52% | Sarah Johnson
PJ002 | HR Digital Onboarding System(Phase I) | Human Resources | Feb 01, 2024 | Mar 31, 2024 | In Progress | $85,000 | $46,750 | 55% | Mark Thompson
PJ003 | Cybersecurity Upgrade Initiative(Q1) | IT Department | Jan 20, 2024 | Mar 15, 2024 | Completed | $67,500 | $63,800 | 100% | Lisa Chen
PJ004 | Remote Work Policy Review & Update(New Framework) | HR & Leadership | Mar 05, 2024 | May 15, 2024 | Pending | $15,000 | $3,250 | 22% | James Reed
PJ005 | Annual Performance Review System Overhaul(Tech Integration) | HR & IT | Feb 28, 2024 | Jun 30, 2024 | In Progress | $115,000 | $67,450 | 59% | Anna Patel