## Worksheet
Office Management - Project Template (Multi-Page)
Project Information
Project Name: | Office Infrastructure Upgrade
Project Code: | OFG-2024-001
Department: | Office Management
Project Manager: | Jane Smith
Status: | In Progress
Timeline
Start Date: | January 15, 2024
End Date: | June 30, 2024
Project Goals & Objectives
1. Upgrade office network infrastructure for improved security and reliability.
2. Redesign workspace layout to increase employee productivity by 25%.
3. Implement new office management software for automated task tracking.
4. Reduce operational costs by 15% within the first year post-implementation.
Project Team Members
Name | Role | Contact
Jane Smith | Project Manager | jane.smith@company.com
Robert Lee | IT Lead | robert.lee@company.com
Lisa Wong | FACILITIES Coordinator | lisa.wong@company.com
Mark Johnson | HR Liaison | mark.johnson@company.com
Responsibility Matrix (RACI)
Task | Project Manager | IT Lead
Network Upgrade Planning | R (Responsible) | A (Accountable)
Workstation Redesign | C (Consulted) | R
Software Implementation | A | R
Budget Monitoring | R | C
Budget Allocation
Infrastructure Upgrade (Network & Cabling) | $45,000
Workspace Redesign (Furniture & Layout) | $68,000
Office Management Software License | $12,500
Training & Onboarding (Team) | $8,000
Contingency Reserve (10%) | $13,350
Total Project Budget | $146,850
Resource Requirements
IT Equipment (Switches, Routers) | 24 units
Furniture Sets (Desks, Chairs) | 50 sets
Software Licenses (Annual) | 60 user licenses
Installation & Setup Staff | 3 full-time for 4 weeks
Project Milestones
Milestone | Due Date | Status
Project Kickoff Meeting | January 15, 2024 | Completed
Network Design Finalized | February 10, 2024 | In Progress
Furniture Procurement Completed | March 5, 2024 | Pending
Workspace Redesign Implementation (Phase 1) | April 10, 2024 | Pending
Office Management Software Deployment | May 15, 2024 | Pending
Final Testing & User Training | June 5, 2024 | Pending
Project Completion & Review Meeting | June 30, 2024 | Pending
Reporting Schedule
Frequency | Report Type | Recipient
Weekly | Status Report (Progress, Risks) | Project Manager & Department Head
Monthly | Budget & Resource Utilization Summary | Finance Department & Executive Team
Quarterly | Milestone Achievement Review & KPI Report | Senior Management Board