## Worksheet
Office Management - Project Timeline (Advanced)
Task ID | Task Name | Description | Start Date | End Date | Status | Assigned To | % Complete
Phase 1: Project Initiation & Planning (Q1)
PI-001 | Project Kickoff Meeting | Formal launch of the office management project with stakeholders. | 2023-04-01 | 2023-04-05 | Completed | Alice Johnson | 100%
PI-002 | Requirement Gathering | Capture functional and non-functional requirements from department heads. | 2023-04-15 | 2023-04-30 | Completed | Robert Lee | 100%
Phase 2: System Design & Architecture (Q2)
SD-001 | Database Schema Design | Create ER diagrams and database structure for office resources. | 2023-05-01 | 2023-05-15 | In Progress | Maria Garcia | 65%
SD-002 | User Interface Wireframes | Design mockups for all key application screens. | 2023-05-10 | 2023-05-31 | In Progress | James Wilson | 80%
Phase 3: Development & Integration (Q3)
DEV-001 | Backend API Development | Implement RESTful services for task and resource management. | 2023-06-15 | 2023-7-31 | In Progress | David Chen | 45%
DEV-002 | Frontend Implementation | Build responsive user interface based on approved wireframes. | 2023-07-15 | 2023-8-31 | Delayed | Sarah Thompson | 30%
Phase 4: Testing, Training & Deployment (Q4)
TST-001 | System Integration Testing | Verify end-to-end functionality across all modules. | 2023-09-15 | 2023-10-15 | Completed | Lisa Park | 100%
TST-002 | User Acceptance Testing (UAT) | Final validation by department representatives. | 2023-10-16 | 2023-11-5 | Delayed | Daniel Rodriguez | 40%
Phase 5: Go-Live & Post-Implementation (Q4)
GL-001 | Production Deployment | Deploy system to live environment with rollback plan. | 2023-11-15 | 2023-11-20 | Completed | Mary Evans | 100%
GL-002 | Post-Implementation Review | Evaluate project success and document lessons learned. | 2023-11-25 | 2023-12-15 | Completed | Alice Johnson | 100%
Project Overview
Total Tasks:12 ¦Completed:8 (67%) ¦In Progress:2 (17%) ¦Delayed:2 (17%)
This project timeline is designed for advanced office management with clear phase breakdowns, real-time status tracking, and comprehensive task assignment.