## Worksheet
Phase | Task | Start Date | End Date | Status | Responsible Team
Planning & Initiation | Define Project Scope | 2024-04-01 | 2024-04-15 | In Progress | Project Management Office (PMO)
| Stakeholder Identification | 2024-04-16 | 2024-04-30 | Pending | HR & Communications
| Risk Assessment & Planning | 2024-05-01 | 2024-05-15 | Pending | Risk Management Team
Execution & Development | Resource Allocation | 2024-05-16 | 2024-06-15 | Pending | HR & Finance Departments
| System Integration Setup | 2024-06-16 | 2024-07-31 | Pending | IT Team
| User Training Modules Development | 2024-08-01 | 2024-08-31 | Pending | Training & Development Unit
Monitoring & Evaluation | Milestone Review: Phase 1 Completion | 2024-05-15 | 2024-05-16 | Completed | PMO & Steering Committee
| Milestone Review: Phase 2 Completion | 2024-07-31 | 2024-08-01 | Completed | PMO & IT Team
| Final Evaluation Report Preparation | 2024-10-01 | 2024-10-15 | Pending | Analysis & Audit Team
Closure & Handover | Closing Documentation & Sign-off | 2024-10-16 | 2024-10-31 | Pending | PMO & Legal Affairs
| Knowledge Transfer to Operations Team | 2024-11-01 | 2024-11-30 | Pending | Operations Management