## Worksheet
Task | Start Date | End Date | Status | Assigned To
Project Initiation | 2024-01-05 | 2024-01-10 | Completed | Jane Smith
Requirement Gathering | 2024-01-11 | 2024-01-25 | In Progress | Mike Johnson
Design Phase | 2024-01-26 | 2024-02-15 | Pending | Sarah Lee
Development Phase | 2024-02-16 | 2024-03-31 | Pending | David Brown
Testing & QA | 2024-04-01 | 2024-04-15 | Pending | Linda Wilson
Deployment | 2024-04-16 | 2024-04-30 | Pending | James Miller
Closure & Review | 2024-05-01 | 2024-05-10 | Pending | Jane Smith