## Worksheet
Project Timeline - Office Management
Task ID | Task Name | Assigned To | Start Date | End Date | Status
TASK001 | Project Initiation & Planning | Alice Johnson | 2024-04-01 | 2024-04-15 | In Progress
TASK002 | Resource Allocation & Team Setup | Robert Lee | 2024-04-16 | 2024-04-30 | Not Started
TASK003 | Office Space Preparation | Sarah Kim | 2024-05-01 | 2024-05-15 | Not Started
TASK004 | IT Infrastructure Setup | James Brown | 2024-05-16 | 2024-05-31 | Not Started
TASK005 | Equipment Procurement & Delivery | Maria Garcia | 2024-06-01 | 2024-06-15 | Not Started
TASK006 | Team Onboarding & Training | Alice Johnson | 2024-06-16 | 2024-06-30 | Not Started
TASK007 | System Integration Testing | James Brown | 2024-07-01 | 2024-07-15 | Not Started
TASK008 | Final Review & Approval | Robert Lee | 2024-07-16 | 2024-07-31 | Not Started
TASK009 | Go-Live & Office Launch | Sarah Kim | 2024-08-01 | 2024-08-15 | Not Started
Created using a Business Use Project Timeline Template for Office Management ¦ Last Updated: April 2024