## Worksheet
Project Name | Phase | Start Date | End Date | Status | Responsible Team
Office Relocation Project | Planning & Design | 2023-10-01 | 2023-10-15 | In Progress | Facilities & HR
Office Relocation Project | Furniture Procurement | 2023-10-16 | 2023-11-05 | Pending | Purchasing Team
Office Relocation Project | Moving & Setup | 2023-11-06 | 2023-11-15 | Not Started | Cleaning & IT Teams
Office Relocation Project | Final Inspection & Handover | 2023-11-16 | 2023-11-20 | Not Started | Facilities & Management
New Software Implementation | Requirements Gathering | 2023-09-15 | 2023-10-05 | Closed | IT & Business Analysts
New Software Implementation | System Development | 2023-10-06 | 2023-11-30 | In Progress | Development Team
New Software Implementation | User Testing & Feedback | 2023-12-01 | 2023-12-15 | Not Started | QA & End Users
New Software Implementation | Deployment & Training | 2023-12-16 | 2023-12-31 | Not Started | IT & HR Teams