## Worksheet
Project Task | Start Date | End Date | Status | Responsible Team
Project Planning & Initiation | 2023-10-01 | 2023-10-15 | In Progress | Management Team
Resource Allocation | 2023-10-16 | 2023-10-25 | Pending | HR & Admin
Design Phase Completion | 2023-10-26 | 2023-11-10 | Pending | Design Team
Development & Implementation | 2023-11-11 | 2024-01-31 | Pending | IT Department
User Testing & Feedback | 2024-02-01 | 2024-02-15 | Pending | QA Team
Final Review & Approval | 2024-02-16 | 2024-02-25 | Pending | Executive Board
Project Launch & Documentation | 2024-03-01 | 2024-03-15 | Pending | Operations Team
Total Duration | 2023-10-01 to 2024-03-15 (6 months)