## Worksheet
Office Management - Project Timeline
Project ID | Project Name | Phase/Task | Start Date | End Date | Duration (Days) | Status
PJ001 | New Office Setup | Site Assessment & Planning | 2023-10-01 | 2023-10-15 | 15 | Completed
PJ001 | New Office Setup | Design Approval & Sign-Off | 2023-10-16 | 2023-10-31 | 16 | Completed
PJ001 | New Office Setup | Furniture Procurement & Delivery | 2023-11-01 | 2023-11-25 | 25 | In Progress
PJ001 | New Office Setup | IT Infrastructure Installation | 2023-11-26 | 2023-12-15 | 20 | Pending
PJ001 | New Office Setup | Moving & Relocation Day | 2023-12-16 | 2023-12-17 | 2 | Pending
PJ001 | New Office Setup | Post-Move Inspection & Handover | 2023-12-18 | 2023-12-25 | 8 | Pending
PJ002 | Annual Office Audit | Schedule & Prepare Audit Team | 2023-11-05 | 2023-11-15 | 11 | Completed
PJ002 | Annual Office Audit | Data Collection & Review | 2023-11-16 | 2023-11-30 | 15 | In Progress
PJ002 | Annual Office Audit | Audit Report Drafting | 2023-12-01 | 2023-12-14 | 14 | Pending
PJ003 | Fleet Management Upgrade | Vendor Selection & Contract Signing | 2023-11-15 | 2023-11-30 | 16 | Completed
PJ003 | Fleet Management Upgrade | Software Implementation & Training | 2023-12-01 | 2024-01-15 | 46 | In Progress
PJ003 | Fleet Management Upgrade | System Evaluation & Final Handover | 2024-01-16 | 2024-01-31 | 16 | Pending
Total Duration (Days): |  |  |  |  | 176
Legend: