## Worksheet
Office Management - Project Timeline
Project ID | Project Name | Department | Milestones & Key Dates |  |  |  | Lead Manager | Status
|  |  | Start Date | Target End Date | Actual End Date | Budget (USD)
Q3 2024 Strategic Office Renovation
PROJ-0891 | Facility Layout Redesign | Facilities & Operations | 2024-07-01 | 2024-08-15 | -- | $75,000 | Sarah Johnson | Ongoing
Key Milestone: Design Approval - August 10, 2024
PROJ-0892 | Furniture Procurement & Delivery | Purchasing & Logistics | 2024-08-16 | 2024-09-15 | -- | $58,750 | Mark Thompson | Delayed (Pending Vendor)
Key Milestone: Delivery Complete - September 15, 2024
PROJ-0893 | IT Infrastructure Upgrade | IT Department | 2024-07-15 | 2024-09-30 | -- | $156,300 | Lisa Chen | Completed (Aug 31)
Q4 2024 Employee Onboarding Initiative
PROJ-0905 | Recruitment Campaign Launch | HR & Talent Acquisition | 2024-10-01 | 2024-11-30 | -- | $45,650 | Daniel Park | Ongoing
Overall Project Progress: 72% Complete ¦ Total Budget: $335,700
Last Updated: October 26, 2024 ¦ Generated via Office Management System