## Worksheet
Project | Task | Start Date | End Date | Responsible | Status
Office Renovation | Design Phase | 2023-10-01 | 2023-10-15 | Jane Doe | Completed
Office Renovation | Procurement | 2023-10-16 | 2023-11-05 | John Smith | In Progress
Office Renovation | Installation | 2023-11-06 | 2023-11-25 | Mike Johnson | Pending
IT System Upgrade | Assessment | 2023-10-05 | 2023-10-20 | Sarah Lee | Completed
IT System Upgrade | Deployment | 2023-10-21 | 2023-11-15 | David Brown | In Progress
IT System Upgrade | Testing | 2023-11-16 | 2023-11-30 | Emma Wilson | Pending
Employee Onboarding | Recruitment | 2023-10-10 | 2023-11-05 | Lisa Chen | In Progress
Employee Onboarding | Training | 2023-11-06 | 2023-11-30 | Tom Harris | Pending