## Worksheet
Project Timeline - Office Management
Project Task | Start Date | End Date | Status | Responsible Person
Define Project Scope & Objectives | 2024-04-01 | 2024-04-05 | In Progress | Jane Doe
Develop Office Layout Plan | 2024-04-06 | 2024-04-15 | Pending | John Smith
Procure Office Furniture & Equipment | 2024-04-16 | 2024-05-10 | Pending | Lisa Wang
Install IT Infrastructure & Networks | 2024-05-11 | 2024-05-25 | Pending | Marcus Lee
Conduct Employee Onboarding Sessions | 2024-05-26 | 2024-06-10 | Pending | Sarah Johnson
Final Inspection & Handover to Team | 2024-06-11 | 2024-06-15 | Pending | Daniel Brown
Template Type: Project Timeline ¦ Purpose: Office Management ¦ Style/Version: Personal Use