## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Progress (%) | Assigned To
PJ-001 | Project Kickoff Meeting | 2024-04-05 | 2024-04-05 | Completed |  | John Smith
PJ-002 | Requirements Gathering | 2024-04-08 | 2024-04-19 | In Progress |  | Alice Johnson
PJ-003 | Requirements Finalized | 2024-04-19 | 2024-04-19 | Completed |  | John Smith
PJ-004 | Design Phase - UI/UX | 2024-04-22 | 2024-05-17 | In Progress |  | Mike Brown
PJ-005 | Design Approval | 2024-05-17 | 2024-05-17 | Pending |  | Team Lead
PJ-006 | Development Phase - Frontend | 2024-05-20 | 2024-06-14 | Delayed |  | Emily Davis
PJ-007 | Development Phase - Backend | 2024-05-20 | 2024-06-14 | Delayed |  | Robert Wilson
PJ-008 | Integration Testing | 2024-06-17 | 2024-06-30 | Not Started |  | QA Team
PJ-009 | User Acceptance Testing (UAT) | 2024-07-01 | 2024-07-15 | Not Started |  | Client & Team
PJ-010 | Project Final Review & Deployment | 2024-07-16 | 2024-07-31 | Not Started |  | Project Manager
© 2024 Office Management System. This is a Planning View of the Project Timeline. All dates are subject to change based on project progress.