## Worksheet
Phase | Task Description | Start Date | End Date | Status | Responsible Team/Person
Project Initiation & Planning
Phase 1 | Define project scope and objectives | 2024-04-01 | 2024-04-05 | In Progress | Jane Doe (PM)
Phase 1 | Stakeholder alignment meeting | 2024-04-06 | 2024-04-15 | Scheduled
Design & Development
Phase 2 | Create office layout design (digital) | 2024-04-16 | 2024-05-15 | Scheduled
Phase 2 | Gather feedback from team leads | 2024-05-16 | 2024-06-15 | Scheduled
Implementation & Deployment
Phase 3 | Procure office furniture and equipment | 2024-06-16 | 2024-07-31 | Scheduled
Phase 3 | Install new infrastructure (network, lighting) | 2024-08-01 | 2024-08-31 | Scheduled
Finalization & Review
Phase 4 | Conduct final walkthrough and QA checks | 2024-09-01 | 2024-09-15 | Scheduled
Phase 4 | Project sign-off and documentation closure | 2024-09-16 | 2024-09-30 | Scheduled