## Worksheet
Project Timeline - Office Management Report
Quarterly Review ¦ Q3 2024 ¦ Prepared on: October 5, 2024
Project Phase | Start Date | End Date | Status | Responsible Team | Milestone Achieved (%)
Project Initiation & Planning | Jul 01, 2024 | Jul 15, 2024 | Completed | Office Management Team | 100%
Resource Allocation & Budgeting | Jul 16, 2024 | Jul 31, 2024 | Completed | Finance & HR Departments | 100%
Furniture Procurement & Delivery | Aug 01, 2024 | Aug 25, 2024 | In Progress | Purchasing Team | 85%
Office Space Design & Layout | Aug 02, 2024 | Aug 31, 2024 | In Progress | Facilities & Design Team | 90%
IT Infrastructure Setup | Aug 15, 2024 | Sep 15, 2024 | In Progress | IT Department | 70%
Moving & Relocation | Sep 16, 2024 | Sep 25, 2024 | Delayed | Operations Team | 30%
Final Inspections & Handover | Sep 26, 2024 | Sep 30, 2024 | Completed | Quality Assurance Team | 100%
Project Summary & Key Insights
Total Duration:92 days (Jul 1 – Sep 30, 2024)
On-Time Completion Rate:71%
Potential Risks:Relocation delay due to logistics coordination issues.
Action Required:Expedite supplier follow-ups and confirm transportation schedule by Oct 8.