## Worksheet
Project Timeline - Office Management
Phase | Task Name | Start Date | End Date | Status | Owner(s)
Planning & Initiation | Define Project Scope & Objectives | 2024-03-01 | 2024-03-05 | Completed | Jane Smith, Tom Reed
Planning & Initiation | Identify Stakeholders & Requirements | 2024-03-06 | 2024-03-15 | Completed | Alex Johnson, Maria Lopez
Design & Development | Create Office Layout & Workflow Diagrams | 2024-03-16 | 2024-03-25 | In Progress
Design & Development | Develop Project Management Dashboard (UI/UX) | 2024-03-18 | 2024-04-15 | In Progress
Implementation & Testing | Deploy Internal Communication System (Slack/Teams Integration) | 2024-04-16 | 2024-05-10 | Pending
Implementation & Testing | Conduct User Acceptance Testing (UAT) | 2024-05-11 | 2024-05-31 | Pending
Closure & Review | Finalize Documentation & Training Materials | 2024-06-01 | 2024-06-15 | Pending
Closure & Review | Project Sign-off and Handover to Operations Team | 2024-06-16 | 2024-06-30 | Pending