## Worksheet
Project | Phase | Start Date | End Date | Status | Budget (USD)
Office Relocation 2024 | Planning & Design | Jan 15, 2024 | Feb 15, 2024 | Completed | $85,000
Office Relocation 2024 | Vendor Selection & Contracts | Feb 16, 2024 | Mar 31, 2024 | In Progress | $45,000
Office Relocation 2024 | Moving & Setup | Apr 1, 2024 | Apr 30, 2024 | In Progress | $160,000
Office Relocation 2024 | Final Inspection & Handover | May 1, 2024 | May 15, 2024 | Delayed | $35,000
Digital Workspace Upgrade | Infrastructure Audit | Feb 1, 2024 | Mar 15, 2024 | Completed | $18,000
Digital Workspace Upgrade | Hardware Procurement | Mar 16, 2024 | Apr 30, 2024 | In Progress | $75,000
Digital Workspace Upgrade | Deployment & Training | May 1, 2024 | Jun 15, 2024 | Delayed | $60,000
Remote Work Policy Implementation | Policy Drafting & Review | Jan 1, 2024 | Feb 15, 2024 | Completed | $5,000
Remote Work Policy Implementation | Employee Onboarding & Training | Feb 16, 2024 | Mar 31, 2024 | Completed | $15,000
Remote Work Policy Implementation | Feedback & Optimization | Apr 1, 2024 | May 31, 2024 | In Progress | $8,000