## Worksheet
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | % Complete
PJ-001 | Office Space Planning & Layout Design | Alice Chen | 2024-04-01 | 2024-04-15 | In Progress | 65%
PJ-002 | IT Infrastructure Setup (Network & Security) | James Reed | 2024-04-05 | 2024-04-30 | In Progress | 85%
PJ-003 | Furniture Procurement & Delivery Coordination | Sophia Martinez | 2024-04-10 | 2024-05-15 | In Progress | 70%
PJ-004 | Employee Onboarding & Training Schedule | David Kim | 2024-05-01 | 2024-05-31 | Completed | 100%
PJ-005 | Office Equipment Installation (Printers, AV Systems) | Laura Bennett | 2024-05-16 | 2024-06-15 | In Progress | 35%
PJ-006 | Final Inspection & Handover to Team Leads | Michael Torres | 2024-06-15 | 2024-06-30 | Delayed | 15%
Note:This timeline is for internal team use. Update statuses regularly to ensure accurate tracking.
Last updated on: 2024-04-15