## Worksheet
Project | Task Description | Assigned To | Start Date | Due Date | Status | % Complete
Q3 Office Renovation Project
Office Renovation | Design Finalization | Jane Smith | 2023-07-01 | 2023-07-15 | On Track | 95%
Office Renovation | Furniture Procurement | Mike Johnson | 2023-07-16 | 2023-08-15 | On Track | 45%
Office Renovation | Construction Phase 1: Demolition | Carlos Rivera | 2023-08-16 | 2023-09-15 | On Track | 15%
Office Renovation | Construction Phase 2: Electrical & Plumbing | Lisa Chen | 2023-09-16 | 2023-10-15 | Near Due Date | 7%
Office Renovation | Interior Finishing & Painting | Daniel Kim | 2023-10-16 | 2023-11-15 | On Track | 0%
Office Renovation | Moving & Setup Finalization | Sarah Wilson | 2023-11-16 | 2023-11-30 | Overdue | 5%
Monthly Operations Review Meeting Preparation
Operations | Data Collection & Reporting | Emily Brown | 2023-11-01 | 2023-11-05 | On Track | 98%
Operations | Review Meeting Agenda Draft | James Taylor | 2023-11-05 | 2023-11-07 | On Track | 65%
Operations | Finalize Presentation Slides | Sophia Martinez | 2023-11-08 | 2023-11-14 | Near Due Date | 40%
Operations | Meeting Conduct & Minutes | Alex Turner | 2023-11-15 | 2023-11-20 | On Track | 7%
Operations | Distribute Follow-Up Actions | Olivia Garcia | 2023-11-20 | 2023-11-30 | On Track | 5%
Q4 Strategic Planning Initiative
Strategic Planning | Market Analysis Research | Natalie White | 2023-10-01 | 2023-11-30 | On Track | 85%
Strategic Planning | Departmental Goal Alignment Workshop | Ryan Davis | 2023-11-25 | 2023-11-30 | Overdue | 65%
Strategic Planning | Craft High-Level Strategy Document | Maria Lopez | 2023-12-01 | 2023-12-15 | On Track | 4%
Strategic Planning | Presentation to Executive Board | David Allen | 2023-12-16 | 2023-12-30 | On Track | 0%