## Worksheet
Office Management Task Manager
Dashboard View - Real-time Task Tracking & Status Monitoring
ID | Task Title | Assigned To | Due Date | Priority | Status | Progress (%)(Current/Total)(Estimate)
001 | Monthly Budget Review | Sarah Johnson | 2025-04-15 | High | In Progress | 68%(3/5)
002 | Office Equipment Upgrade | David Chen | 2025-04-18 | Medium | Not Started | 0%(0/4)
003 | Team Offsite Planning | Lisa Rodriguez | 2025-04-12 | High | Completed | 100%(5/5)
004 | IT Security Audit | James Wilson | 2025-04-10 | High | Overdue | 85%(7/8)
005 | Employee Onboarding Process | Amy Patel | 2025-04-14 | Medium | In Progress | 45%(3/7)
006 | Website Redesign Proposal | Marcus Brown | 2025-04-20 | Low | Not Started | 15%(3/20)
Total Tasks:6 ¦Completed:1 ¦In Progress:2 ¦Overdue:1