## Worksheet
Task ID | Task Name | Assigned To | Timeline |  |  | Status | Priority
|  |  | Start Date | Due Date | Duration (Days)
001 | Project Planning Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | 3 | In Progress | High
002 | Office Space Setup | John Doe | 2024-04-05 | 2024-04-15 | 11 | To Do | High
003 | IT Infrastructure Deployment | Alice Johnson(Backup: Bob Lee) | 2024-04-10 | 2024-04-30 | 21 | Not Started | Urgent
004 | Employee Onboarding Process | Lisa Brown(Support: Mark Taylor) | 2024-05-01 | 2024-05-15 | 15 | To Do | Medium
005 | Monthly Budget Review | Emily Davis(Review by Finance) | 2024-05-20 | 2024-05-31 | 12 | To Do | Medium
Total Tasks | [5 empty] | 5