## Worksheet
Operations Dashboard - Client View
Project ID | Client Name | Service Type | Status | Start Date | Expected End Date | Progress (%) | Milestone Achieved (Last)
P00123 | GlobalTech Solutions | Data Migration & Integration | Completed | Jan 5, 2024 | Feb 10, 2024 | 100% | Data Sync Finalized & Verified
P00189 | FutureFinance Inc. | Cloud Infrastructure Setup | Completed | Feb 1, 2024 | Mar 15, 2024 | 100% | Production Environment Live & Monitored
P00345 | MarketWave Analytics | Custom Dashboard Development | In Progress | Feb 15, 2024 | Apr 30, 2024 | 68% | User Interface Design Approved
P00456 | NexaHealth Systems | API Integration & Testing | Delayed | Jan 22, 2024 | Mar 8, 2024 | 35% | Authentication Module Development
P00678 | BrightStar Retail | Inventory Management System Upgrade | In Progress | Mar 5, 2024 | May 10, 2024 | 45% | Database Schema Updated
Active Projects
4Completed Projects
2On Track
2Delayed Projects