## Operations Dashboard
Operations Dashboard
Department | Project Name | Status | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | % Complete
Sales & Marketing | Q4 Campaign Launch | In Progress | 2023-10-01 | 2023-12-31 | 2023-10-05 | - | 75%
Product Development | New Feature Rollout v2.1 | In Progress | 2023-11-15 | 2024-01-30 | 2023-11-20 | - | 65%
IT Support | System Upgrade Phase 2 | Delayed | 2023-12-01 | 2023-12-15 | 2023-12-18 | - | 45%
Human Resources | Talent Acquisition Drive 2024 | Planning | 2023-11-01 | 2024-03-31 | - | - | 5%
Total Projects Overview | [6 empty] | 62%
Key Performance Indicators (KPIs)
KPI | Target | Current | Variance
On-Time Delivery Rate | 95% | 92% | -3.0%
Customer Satisfaction (CSAT) | 90/100 | 87/100 | -3
Resource Utilization | 85% | 82% | -3.0%
Bug Resolution Time | < 48 hrs | 56 hrs | +8 hrs
Operations Dashboard ¦ Updated on October 25, 2023 ¦ Version 1.0