## Worksheet
Operations Dashboard
Gantt Chart - Analysis View (Q3 2024)
Task ID | Project Phase | Description | Start Date | End Date | Status | Progress (%) | Timeline (Gantt View)
PRJ-001 | Requirement Analysis | Finalize user requirements and system specs | 2024-07-01 | 2024-07-15 | On Track |  | 7/17/16
PRJ-002 | Design Phase | UI/UX and system architecture design | 2024-07-16 | 2024-08-15 | Active |  | 7/16
PRJ-003 | Development | Backend and frontend development cycles | 2024-08-16 | 2024-10-31 | Delayed |  | 8/16
PRJ-004 | Testing & QA | Integration, UAT, and bug fixing | 2024-11-01 | 2024-11-30 | On Track |  | 11/1
PRJ-005 | Deployment & Training | Go-live, user onboarding, documentation | 2024-12-01 | 2024-12-31 | On Track |  | 12/1
Overall Project Status | [5 empty] | 73% | Progress Summary: