## Worksheet
Operations Dashboard - Gantt Chart
Task ID | Task Name | Start Date | End Date | Status | Progress (%)
T001 | Project Initiation | 2024-01-05 | 2024-01-15 | In Progress
T002 | Requirements Gathering | 2024-01-16 | 2024-01-31 | In Progress
T003 | System Design | 2024-02-01 | 2024-02-15 | Not Started
T004 | Development Phase 1 | 2024-02-16 | 2024-03-15 | Not Started
T005 | Testing & QA | 2024-03-16 | 2024-04-15 | Not Started
T006 | Deployment | 2024-04-16 | 2024-04-30 | Not Started
T007 | Post-Deployment Review | 2024-05-01 | 2024-05-15 | Not Started
Note: This Gantt chart is a simplified representation. Actual project timelines may vary.