## Worksheet
Operations Dashboard
Gantt Chart - Project Timeline Overview
Task | Start Date | End Date | Progress | Status | Timeline (Day Grid)
Project Initiation | 2024-04-01 | 2024-04-15 |  | Completed | April 1 - April 15
Requirements Gathering | 2024-04-16 | 2024-05-15 |  | In Progress | April 16 - April 30 | May 1 - May 15
Design Phase | 2024-05-16 | 2024-06-30 |  | In Progress | May 16 - May 31 |  |  | June 1 - June 30
Development Phase | 2024-07-01 | 2024-10-31 |  | In Progress | July 1 - July 31 |  |  |  | Aug 1 - Aug 31 |  | Oct 1 - Oct 31
Testing & QA | 2024-10-01 | 2024-11-30 |  | In Progress | Oct 1 - Oct 31 |  |  |  |  | Nov 1 - Nov 30
Deployment & Go-Live | 2024-11-01 | 2024-12-31 |  | In Progress | Nov 1 - Nov 30 |  | Dec 1 - Dec 31
Post-Deployment Review | 2025-01-01 | 2025-01-31 |  | Delayed | Jan 1 - Jan 31
Key:Completed ¦ In Progress ¦ Delayed