## Worksheet
Operations Dashboard - Gantt Chart (Extended)
Task Name | Timeline |  |  |  |  | Status | Progress | Owner
| Start Date | Due Date | Duration (Days) | Progress Period | Gantt View
Project Planning & Initiation | 2024-03-01 | 2024-03-15 | 15 days | Mar 1 - Mar 15 |  | Completed |  | Anna Reed
Resource Allocation & Budgeting | 2024-03-16 | 2024-03-31 | 16 days | Mar 16 - Mar 31 |  | In Progress |  | James Wilson
Design Phase - UI/UX | 2024-04-01 | 2024-05-15 | 45 days | Apr 1 - May 15 |  | In Progress |  | Sophia Martinez
Development Sprint #1 | 2024-05-16 | 2024-06-30 | 45 days | May 16 - Jun 30 |  | In Progress |  | David Kim
Testing & QA Phase | 2024-07-01 | 2024-08-15 | 46 days | Jul 1 - Aug 15 |  | Delayed |  | Laura Brown
Deployment & Go-Live | 2024-08-16 | 2024-09-30 | 45 days | Aug 16 - Sep 30 |  | Not Started |  | Marcus Lee
Post-Launch Support & Review | 2024-10-01 | 2024-11-30 | 61 days | Oct 1 - Nov 30 |  | Not Started |  | Amy Patel
Overall Project Status | [5 empty] | On Track |  | Project Lead: Sarah Johnson