## Worksheet
Operations Dashboard
Gantt Chart - Financial View (Q3 2024)
Project / Task | Start Date | End Date | Status | Progress (%) | Budget (USD) | Actual Spend (USD)
Product Launch Phase 1 | 2024-07-01 | 2024-08-31 | In Progress | 75% | $1,200,000 | $892,456
Marketing Campaign Q3 | 2024-07-15 | 2024-09-30 | In Progress | 60% | $850,000 | $523,791
Infrastructure Upgrade | 2024-08-01 | 2024-11-30 | In Progress | 45% | $2,500,000 | $1,125,341
Customer Onboarding Portal | 2024-09-01 | 2024-11-30 | In Progress | 35% | $980,000 | $342,178
Vendor Contract Renewal | 2024-07-10 | 2024-10-15 | Completed | 100% | $425,000 | $425,367
Internal Audit & Compliance | 2024-10-01 | 2024-11-30 | Delayed | 25% | $310,000 | $78,643
New Hire Training Program | 2024-08-15 | 2024-10-31 | In Progress | 65% | $180,000 | $117,432
System Migration (Phase 2) | 2024-09-05 | 2024-11-30 | Delayed | 40% | $1,850,000 | $753,291
Total Project Summary | Aggregated Metrics |  |  |  | $9,295,000 | $4,837,538
Last updated on October 26, 2024 ¦ Data reflects financial and timeline performance across Q3 operations.