## Worksheet
Operations Dashboard - Gantt Chart
Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
Data Integration Setup | 2025-04-01 | 2025-04-15 | 14 | On Track
System Testing Phase | 2025-04-16 | 2025-04-30 | 15 | On Track
User Training Sessions | 2025-05-01 | 2025-05-14 | 14 | On Track
Go-Live Launch | 2025-05-15 | 2025-05-15 | 1 | On Track
Post-Launch Review | 2025-05-16 | 2025-05-31 | 16 | On Track
Performance Optimization | 2025-06-01 | 2025-06-30 | 30 | On Track
Q2 Project Closeout | 2025-06-30 | 2025-06-30 | 1 | On Track
Monthly Report Preparation | 2025-07-01 | 2025-07-31 | 31 | On Track