## Worksheet
Operations Dashboard - Gantt Chart (Page 1)
Project | Task | Start Date | End Date | Duration (Days) | Status | Progress
Project Alpha | Requirement Gathering | 2024-03-01 | 2024-03-15 | 15 | In Progress
| Design Phase | 2024-03-16 | 2024-03-31 | 16 | In Progress
| Development Phase | 2024-04-01 | 2024-05-15 | 45 | Not Started
| Testing & QA | 2024-05-16 | 2024-06-30 | 45 | Not Started
Project Beta | Architecture Review | 2024-04-01 | 2024-04-15 | 15 | In Progress
| Backend Development | 2024-04-16 | 2024-06-30 | 75 | In Progress
| Frontend Integration | 2024-07-01 | 2024-08-15 | 45 | Not Started
Operations Dashboard - Gantt Chart (Page 2)
Project | Task | Start Date | End Date | Duration (Days) | Status | Progress
Project Gamma | Data Migration Setup | 2024-03-10 | 2024-03-31 | 22 | In Progress
| Data Extraction & Transformation | 2024-04-01 | 2024-05-31 | 61 | In Progress
| Data Validation & Cleansing | 2024-06-01 | 2024-07-15 | 45 | In Progress
| Final Deployment & UAT | 2024-07-16 | 2024-08-31 | 46 | Not Started
Project Delta | Infrastructure Setup | 2024-05-15 | 2024-06-30 | 46 | In Progress
| Security & Compliance Audit | 2024-07-01 | 2024-08-31 | 61 | In Progress
| Production Rollout | 2024-09-01 | 2024-10-31 | 61 | Not Started
Project Summary
Project | Total Tasks | Completed | In Progress | Not Started | Avg. Progress (%)
Project Alpha | 4 | 0 | 2 | 2 | 67.5%
Project Beta | 3 | 0 | 2 | 1 | 65.0%
Project Gamma | 4 | 0 | 3 | 1 | 75.8%
Project Delta | 3 | 0 | 2 | 1 | 52.5%
Legend:
In Progress - Task is actively being worked on.
Not Started - Task has not yet begun.