## Worksheet
Operations Dashboard
Gantt Chart - Office Use Template
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress
001 | Project Planning & Requirements Gathering | 2025-04-01 | 2025-04-15 | 15 | Completed
002 | Design Phase - UI/UX Development | 2025-04-16 | 2025-05-14 | 30 | In Progress
003 | Backend System Development | 2025-05-15 | 2025-06-30 | 47 | In Progress
004 | Frontend Integration & Testing | 2025-07-01 | 2025-07-15 | 15 | In Progress
005 | User Acceptance Testing (UAT) | 2025-07-16 | 2025-07-31 | 16 | Delayed
006 | Deployment & Go-Live | 2025-08-01 | 2025-08-15 | 15 | Completed
007 | Post-Launch Review & Optimization | 2025-08-16 | 2025-08-31 | 16 | In Progress